## Sheet1
PHI Omega Preparations for Super Regional 2-19-15
Priorities:
Excellent Drivers
At least 2 hours driver practice per meeting
Excellent Robot
Using quality control
Allowing only small changes (implemented in < 30 minutes per meeting)
Provide spare assemblies as appropriate
Excellent Notebook
Excellent Autonomy
Tasks and Notes:
Find out who can travel to Oakland for Super Regional
Clean the Stinson's garage and keep it clean
Driver practice every week with priority for travellers
Notebook work
Increase autonomy points
Consider creating a "Built-in-Test" module in the control laws
Top bucket
Replace top strap with a solid strip from NASA
Fab Spare Bucket - small team working independent of the robot
Vertical Slide
Build a working unit from 80-20 materials independent of the robot
Done by a small independent team
Replace lateral brace on vertical slide
Replace all Tamiya power connectors with Anderson Power Pole Connectors
On robot wiring harness and all batteries
Ferrite Choke on Cable from Samantha to NXT
Fastener Retention
Install better locknuts, Locktite, Nail Polish (Torque Stripes)as appropriate
This caused a jammed wheel during one match
Positive String Tension
Rig string with min slack
Add string tensioner
Buy a battery tester from Andy Mark
Buy Anderson Power Pole connectors from Andy Mark
Buy 80-20 slide parts
Add a small water spray bottle to the Away Kit (as a backup to the mister)
Add a box of dryer sheets to the Away Kit
Practice using a pre-match checklist as part of driver practice
Alpha could provide some of the small independent teams

## Schedule
Category | Item | Date Started | Projected Completion | Date Completed | POC | Notes
Notebook | Highlights Summary of Competion | 2015-02-23 | 2015-02-23 |  | Kaitlin | Summary sheet highlighting how team got to super-regional.
| Enhance Outreach with FLL | 2015-02-19 | 2015-02-23 |  | Kaitlin
| Maintain daily logs with pics | 2015-02-19 | 2015-03-27 |  | Kaitlin | Team contributions required. Document with pics.
Highlight innovation with summary assessment
Hardware | Evaluate 80/20's with mock up | 2015-02-19 | 2015-03-05 | 2015-02-19 | Eddie | Decision was made to forego 80/20's due to expense, and instead improve reliability of current linear slides.
Insert Ferrhite choke on NXT-Samantha cable
| Make spare bucket (1) | 2015-02-19 | 2015-02-23 |  | Sergei
| Make spare belts | 2015-02-19 | 2015-02-23 |  | Eddie
Make spare belt roller
| Make spare back flap | 2015-02-19 | 2015-02-26 |  | Sergei | Completed two but could be improved
Replace fasteners with better lock nuts, locktite, etc
Add string tensioner to wench cable
| Replace lateral brace on top of bucket | 2015-02-19 | 2015-02-25 |  | Jonathon
ReplaceTamiya power connectors with Anderson Power Pole Connectors
Software | Install 'Nanny' chip for NXT freezing mitigation |  |  |  |  | Decision was made to forego
Tweak the ramp and parking zone autonomy for better ball score
Work with hardware to investigate anolamous wench encoder reading
Develop autonomy to nail the IR center goal
Fundraising | Develop ideas for quick fund raising | 2015-02-19 | 2015-03-02 |  | Holly | Team contributions required.
| Contact and evaluate ideas | 2015-03-02 | 2015-03-05 |  | Holly | Team contributions required.
| Conduct fundraising | 2015-03-05 | 2015-03-19 |  | Holly | Team contributions required.
Miscellaneous | Add spray bottle with soap to packing list
Add dryer sheets to packing list
Update match checklist with de-static process
| Brochure | 2015-02-19 | 2015-02-26 |  | Becky/Holly